## Sheet1
High Level Overview / Process Steps / Timing
| Saturday 8/22/2020 | Tuesday 8/25/2020 | Thursday 8/27/2020 |  | Saturday 8/29/2020
Step 1 - Finalize and cleanup data
Step 2 - Geocode data for mapping visualizations
Step 3 - Establish what maps/visualizations we would like to do
Step 4 - Create maps and visualizations
Step 5 - Develop dashboard to display maps and visualizations
Step 6 - Create narratives for maps and visualizations
Step 7 - Place narratives, maps, visualizations onto dashboard
Step 8 - Ensure project requirements are met
Step 9 - Develop presentation
Step 10 - Presentation
Step 11 - Finalize all work and submit
Detail Process Steps / Team Responsibilities
Process Step | Description |  |  | Team Members
Finalize and cleanup data | Need to establish which data from original ETL project we will be using and remove unnecessary data |  |  | All
Geocode data for mapping visualizations | Need to add geocoded data to existing data so that data can be mapped |  |  | Katie
Establish which maps/visualizations we will use | Need to pick which types of visualizations we will be using and what data will be visualized for each separate visualization |  |  | All
| Type of Visualization | Data Used/Comparison Being Made | Team Member
Create maps and visualizations | Once visualizations that will be used are established, create each map and visualization |  |  | All
Develop dashboard | Need web dashboard to display visualizations and narratives |  |  | Polina
Create narratives for maps and visualizations | For each map/visualization that is created a related narrative will also need to be drafted |  |  | All
Place narratives, maps, visualizations onto dashboard | Place all content onto dashboard and ensure functionality |  |  | All
Ensure project requirements are met | Double check to make sure that all necessary components for project are present |  |  | Emmanuel
Develop presentation | Need to develop power point slides and practice presentation |  |  | Michelle
Presentation | Class presentation - 8/29/2020 |  |  | All
Finalize all work and submit | Need to make sure that all components are in github repo and are submitted on time |  |  | Polina